## Website Audit
Website Storefront Audit — STAGING BUILD REVIEW
Valdosta Dental Associates ¦ Staging: https://valdostadentalassociates.kinsta.cloud/ ¦ Live: https://www.thevaldostadentist.com/ ¦ Audited 2026-07-20
Question answered: Is the new website build ready to replace the live site — and where does it need work before launch?
Practice Name | Website URL | Audit Section | Audit Item | Status | NEW STATUS | Dev Notes | Growth Manager | Evidence Found | Detected URL | Notes | Priority | Recommended Fix | Tool Used | Confidence
Technical Health — Weight 15% • Section score 62/100 (13 scored, 1 manual review)
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | HTTPS enabled | Pass |  |  |  | Site served over HTTPS; HTTP 200 | https://valdostadentalassociates.kinsta.cloud/ |  | Low | None — already compliant | curl / headers | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | Homepage loads successfully | Pass |  |  |  | HTTP 200; 532,210 bytes of HTML delivered | https://valdostadentalassociates.kinsta.cloud/ | WordPress 7.0.2 + Elementor 4.1.5 + WP Rocket on Kinsta | Low | None | curl | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | Mobile responsive viewport | Pass |  |  |  | viewport meta: width=device-width, initial-scale=1 (zoom NOT disabled) | https://valdostadentalassociates.kinsta.cloud/ |  | Low | None | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | PSI mobile performance | Partial |  |  |  | PSI mobile Performance = 77/100 (second run 82). LCP 3.8s, CLS 0.035, TBT 0ms | https://valdostadentalassociates.kinsta.cloud/ | Better than live site (63) but LCP above 2.5s target; hero is a 2560px AdobeStock JPEG | Medium | Serve appropriately sized hero image; preload LCP image | PageSpeed Insights API (mobile) | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | PSI accessibility | Partial |  |  |  | PSI mobile Accessibility = 85/100 | https://valdostadentalassociates.kinsta.cloud/ | Empty alt text on all 10 homepage images is the main driver | High | Add descriptive alt text to all content images | PageSpeed Insights API | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | PSI best practices | Pass |  |  |  | PSI mobile Best Practices = 100/100 | https://valdostadentalassociates.kinsta.cloud/ | Live site scores 65 | Low | Maintain | PageSpeed Insights API | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | PSI SEO score | Partial |  |  |  | PSI mobile SEO = 61/100 — depressed by staging noindex header | https://valdostadentalassociates.kinsta.cloud/ | Score is artificially low while X-Robots-Tag: noindex is active; re-test after launch | Medium | Re-run PSI after launch when indexing is enabled | PageSpeed Insights API | Medium
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | Broken internal links | Partial |  |  |  | 26 internal URLs crawled; 1 broken: /preventive-care/ (404) linked from homepage nav — misspelling of /preventative-care/ | https://valdostadentalassociates.kinsta.cloud/preventive-care/ | All other nav/footer links resolve 200 | High | Fix nav link to point to /preventative-care/ | curl full-site crawl | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | XML sitemap exists | Partial |  |  |  | Rank Math sitemap_index.xml present with post/page/category/local sub-sitemaps | https://valdostadentalassociates.kinsta.cloud/sitemap_index.xml | Sitemap still contains default WP cruft: /hello-world/ post and /category/uncategorized/ | Medium | Delete Hello World post + Uncategorized archive before launch | curl | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | robots.txt exists | Pass |  |  |  | robots.txt present; references sitemap_index.xml; blocks only /wp-admin/ | https://valdostadentalassociates.kinsta.cloud/robots.txt |  | Low | None | curl | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | Index controls launch-ready | Needs Manual Review |  |  |  | Server sends X-Robots-Tag: noindex, nofollow, nosnippet, noarchive (Kinsta staging default). On-page meta robots says index, follow | https://valdostadentalassociates.kinsta.cloud/ | Correct for staging — but MUST be removed when the site moves to the production domain, and verified in GSC | High | Add 'verify noindex removed' to the launch checklist; confirm header on production domain day 1 | curl headers | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | 301 redirect map from legacy URLs | Fail |  |  |  | Legacy live-site paths 404 on the new build: /contact-us, /my-blog, /appointment-request, /services, /extractions-with-iv-sedation, /disclaimers/* all return 404 | https://valdostadentalassociates.kinsta.cloud/ | Old site ranks for these URLs today; without 301s all Google equity and bookmarked links break at cutover | High | Build a 301 map for all 18 legacy URLs before launch (see Live vs Staging sheet) | curl status probe | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | Homepage metadata accuracy | Fail |  |  |  | title = 'Home - Valdosta Dental Associates' — no keyword, no city | https://valdostadentalassociates.kinsta.cloud/ | Live site title includes 'Valdosta, GA Dentist'. Meta description is good (162 chars w/ CTA) | High | Set title to 'Dentist in Valdosta, GA ¦ Valdosta Dental Associates' (<65 chars) | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Technical Health | Local schema markup | Partial |  |  |  | JSON-LD Dentist schema present, but openingHours = Mon–Sun 09:00–17:00 (open 7 days incl. weekend — almost certainly wrong) | https://valdostadentalassociates.kinsta.cloud/ | Live site schema: MedicalBusiness + Dentist | High | Correct schema hours to actual office hours; verify against GBP | HTML inspection | High
Conversion & Contact — Weight 25% • Section score 70/100 (10 scored, 2 manual review)
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | Scheduling CTA present | Pass |  |  |  | 'Request Appointment' CTA in header links to /contact/; 5 booking-CTA instances on homepage | https://valdostadentalassociates.kinsta.cloud/ |  | Low | Maintain | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | Appointment button visible above the fold | Needs Manual Review |  |  |  | Header CTA present in markup; rendered position not verified | https://valdostadentalassociates.kinsta.cloud/ | Requires a rendered-device check | Medium | Verify CTA renders above the fold on mobile | Manual review | Medium
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | Phone number in header | Pass |  |  |  | (229) 249-0717 present in header area | https://valdostadentalassociates.kinsta.cloud/ | Same tracking-free number as live site & GBP | Low | None | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | Click-to-call enabled | Pass |  |  |  | tel: link present: tel:(229) 249-0717 | https://valdostadentalassociates.kinsta.cloud/ | href works but contains encoded spaces/parens — cosmetic cleanup to tel:+12292490717 | Low | Normalize tel href to E.164 format | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | Sticky mobile CTA | Needs Manual Review |  |  |  | Cannot confirm sticky/floating CTA from static HTML | https://valdostadentalassociates.kinsta.cloud/ | Requires a rendered-device check | Medium | Verify sticky call/book bar on mobile | Manual review | Medium
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | Appointment request form | Pass |  |  |  | Gravity Forms form (gform_1) embedded on /contact/ and /new-patients/ | https://valdostadentalassociates.kinsta.cloud/contact/ | Same form reused on both pages | Low | None | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | Form is short (≤5 fields) | Partial |  |  |  | Form has 6 input fields | https://valdostadentalassociates.kinsta.cloud/contact/ | Slightly over the 5-field target | Low | Trim to name / phone / email / message if possible | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | True online scheduling vs lead form | Fail |  |  |  | No real-time scheduler (NexHealth/LocalMed/etc.) — lead form only | https://valdostadentalassociates.kinsta.cloud/ | Consistent with crosswalk: Scheduler Live = 'Not Live' for VDC/VDO. Same gap exists on live site | Medium | Roadmap item: add online scheduling when practice enables a scheduler | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | New patient offer / special | Fail |  |  |  | No new-patient offer detected on staging (none on live either) | https://valdostadentalassociates.kinsta.cloud/ | Significant conversion opportunity on a brand-new build | High | Add a specific new-patient offer with CTA to homepage + new-patients page | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | Multiple contact methods | Partial |  |  |  | Phone + form; no chat/chatbot | https://valdostadentalassociates.kinsta.cloud/ |  | Low | Consider chat widget post-launch | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | Emergency appointments promoted | Pass |  |  |  | Dedicated /emergency-appointments/ page; promoted from homepage hero icons | https://valdostadentalassociates.kinsta.cloud/emergency-appointments/ | Carried over from live site | Low | Maintain | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Conversion & Contact | Contact page completeness | Pass |  |  |  | Form + embedded Google Map + address on /contact/ | https://valdostadentalassociates.kinsta.cloud/contact/ |  | Low | None | HTML inspection | High
Location Information — Weight 10% • Section score 90/100 (5 scored, 2 manual review)
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Location Information | NAP visible on site | Pass |  |  |  | 103 W. Cranford Ave., Valdosta, GA 31602 + (229) 249-0717 in footer/contact | https://valdostadentalassociates.kinsta.cloud/ | Matches GBP exactly (103 W Cranford Ave) | Low | None | HTML inspection + SerpAPI | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Location Information | Address matches Google Business Profile | Pass |  |  |  | GBP: 103 W Cranford Ave, Valdosta, GA 31602 — exact match | https://valdostadentalassociates.kinsta.cloud/ | GBP rating 4.3★, 197 reviews | Low | None | SerpAPI | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Location Information | Embedded Google Map | Pass |  |  |  | Live Google Maps embed on homepage and contact page | https://valdostadentalassociates.kinsta.cloud/ |  | Low | None | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Location Information | Hours accurate and displayed | Needs Manual Review |  |  |  | Schema hours say Mon–Sun 09:00–17:00 (7 days). Visible hours block not confirmed in rendered page | https://valdostadentalassociates.kinsta.cloud/ | A dental office open Sat+Sun 9–5 is almost certainly a template default | High | Display real hours on contact page; fix schema to match | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Location Information | Second location (Oak St) represented | Needs Manual Review |  |  |  | 3119 N Oak Street Extension (VDO) appears NOWHERE on the new build | https://valdostadentalassociates.kinsta.cloud/ | NOT a regression — live site also omits Oak St. Both VDC and VDO share this domain in the crosswalk. Decide deliberately whether the new site should present both locations | Medium | Confirm with practice/GM whether Oak St should have a location page on the new site | Full-text grep of all fetched pages | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Location Information | Location-specific URL | Partial |  |  |  | Single-location site; /contact/ doubles as the location page | https://valdostadentalassociates.kinsta.cloud/contact/ | Fine for one location; revisit if Oak St is added | Low | None unless Oak St added | HTML inspection | Medium
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Location Information | Directions link | Pass |  |  |  | Google Maps directions link present | https://valdostadentalassociates.kinsta.cloud/ |  | Low | None | HTML inspection | High
Services — Weight 15% • Section score 67/100 (6 scored, 1 manual review)
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Services | Services clearly listed | Pass |  |  |  | Mega-menu organizes services under General / Cosmetic / Prosthodontics / Endodontic / Oral Surgery / Periodontal / Preventative | https://valdostadentalassociates.kinsta.cloud/ | Major upgrade vs live site's single /services page | Low | Maintain | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Services | Individual service pages exist | Pass |  |  |  | 13 dedicated service pages (fillings, bridges, crowns, bonding, sealants, whitening, veneers, dentures, root canal, extractions, scaling & root planing, IV sedation, preventative care) | https://valdostadentalassociates.kinsta.cloud/ | Live site has ~4 service-related pages; this is the single biggest SEO gain of the rebuild | Low | Maintain | Sitemap + crawl | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Services | High-value procedures covered | Partial |  |  |  | Whitening, veneers, crowns, dentures, IV sedation all have pages — but NO dental implants page and NO Invisalign/clear-aligner page | https://valdostadentalassociates.kinsta.cloud/ | Implants + aligners are the two highest-value search terms in most markets | High | Add /dental-implants/ and /invisalign/ (or clear-aligners) pages if services are offered | Sitemap review | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Services | Emergency dentistry content | Pass |  |  |  | /emergency-appointments/ page with same-day messaging | https://valdostadentalassociates.kinsta.cloud/emergency-appointments/ |  | Low | Maintain | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Services | Cosmetic services aspirational + visual | Partial |  |  |  | Cosmetic pages exist but no before/after imagery — live site's /smile-gallery was dropped | https://valdostadentalassociates.kinsta.cloud/cosmetic-dentistry/ |  | Medium | Rebuild smile gallery (or embed on cosmetic pages) | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Services | FAQs on service pages | Fail |  |  |  | No FAQ content or FAQ schema found on sampled service pages | https://valdostadentalassociates.kinsta.cloud/general-dentistry/ |  | Medium | Add 3–5 FAQs w/ schema per major service page | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Services | Patient-friendly language | Needs Manual Review |  |  |  | Copy tone not fully assessed from static HTML | https://valdostadentalassociates.kinsta.cloud/ | Spot-checks look patient-friendly ('Superior dentistry with a personal touch') | Low | Editorial review pass | Manual review | Medium
Doctor / Team Trust — Weight 10% • Section score 60/100 (5 scored, 1 manual review)
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Doctor / Team Trust | Doctor bios present | Pass |  |  |  | 5 doctor bios: Dr. Grantham, Dr. Holloway, Dr. Stites, Dr. Lairsey, Dr. Carter (DMD/DDS) with education + personal stories | https://valdostadentalassociates.kinsta.cloud/staff/ | MAJOR upgrade — live site /staff has no individual bios at all | Low | Maintain | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Doctor / Team Trust | Doctor credentials shown | Pass |  |  |  | DMD/DDS credentials and dental-school education in each bio | https://valdostadentalassociates.kinsta.cloud/staff/ |  | Low | None | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Doctor / Team Trust | Personal/community stories | Pass |  |  |  | Bios include hometown, family, church/community involvement | https://valdostadentalassociates.kinsta.cloud/staff/ | Strong local-trust content for a South-Georgia market | Low | None | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Doctor / Team Trust | Real photos (not stock) of doctors/team | Needs Manual Review |  |  |  | Photo files present on staff page; whether they are professional headshots vs stock not verified visually | https://valdostadentalassociates.kinsta.cloud/staff/ | Homepage hero uses AdobeStock imagery; logo asset is literally named 'Screenshot-2026-07-08-at-10.47.28-AM.png' | Medium | Verify headshots; replace stock hero with real office/team photography; export a proper logo file | Manual review | Medium
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Doctor / Team Trust | Technology/equipment featured | Fail |  |  |  | No technology content detected (CEREC, digital X-ray, iTero, etc.) | https://valdostadentalassociates.kinsta.cloud/ |  | Low | Add a technology section if applicable | HTML inspection | Medium
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Doctor / Team Trust | Awards / affiliations displayed | Fail |  |  |  | No ADA/AGD/association badges detected | https://valdostadentalassociates.kinsta.cloud/ |  | Low | Add association logos to footer/about | HTML inspection | Medium
Patient Resources — Weight 10% • Section score 36/100 (7 scored, 0 manual review)
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Patient Resources | New Patients page | Pass |  |  |  | /new-patients/ with embedded appointment form | https://valdostadentalassociates.kinsta.cloud/new-patients/ |  | Low | Maintain | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Patient Resources | Insurance information | Partial |  |  |  | 'We accept most insurance programs including Medicaid & Peachstate' — only 2 plans named | https://valdostadentalassociates.kinsta.cloud/ | Same generic depth as live site | Medium | List major accepted plans (Delta, Cigna, MetLife, etc.) | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Patient Resources | Financing options | Fail |  |  |  | No CareCredit/Sunbit/Cherry or payment-plan content anywhere | https://valdostadentalassociates.kinsta.cloud/ | Same gap on live site | Medium | Add financing section w/ vendor logos if offered | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Patient Resources | Membership plan for uninsured | Fail |  |  |  | No in-house membership plan content | https://valdostadentalassociates.kinsta.cloud/ | Crosswalk: no Plan Forward for VDC/VDO | Low | N/A unless practice launches a plan | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Patient Resources | Patient education library | Fail |  |  |  | Live site's /patient-education (Officite licensed library) was NOT carried over | https://valdostadentalassociates.kinsta.cloud/ | Likely intentional — Officite content is licensed to their platform — but confirm it is a deliberate drop | Low | Confirm intentional; optionally replace with blog content over time | Crawl comparison | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Patient Resources | Kids' preventative content | Pass |  |  |  | /preventative-tips-for-children/ carried over from live site | https://valdostadentalassociates.kinsta.cloud/preventative-tips-for-children/ |  | Low | Maintain | Crawl | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Patient Resources | Blog active | Fail |  |  |  | /blog/ exists but contains only the default 'Hello World!' post | https://valdostadentalassociates.kinsta.cloud/blog/ | Live site's /my-blog is also empty — no content loss, but placeholder must not launch | Medium | Delete Hello World; seed 2–3 launch posts or hide blog until content exists | Crawl | High
Social Proof — Weight 5% • Section score 0/100 (5 scored, 0 manual review)
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Social Proof | Patient reviews on website | Fail |  |  |  | No reviews/testimonials on staging. A commented-out 'Reviews' block exists in the homepage HTML — the section was built then disabled. Live site HAS a /reviews page | https://valdostadentalassociates.kinsta.cloud/ | GBP has 4.3★ / 197 reviews ready to showcase | High | Re-enable/rebuild the reviews section or a /reviews page with Google review embeds | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Social Proof | Link to Google profile for reviews | Fail |  |  |  | No 'review us' / Google profile link detected | https://valdostadentalassociates.kinsta.cloud/ |  | Medium | Add Google review link in footer | HTML inspection | Medium
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Social Proof | Before/after smile gallery | Fail |  |  |  | Live /smile-gallery page dropped; no before/after imagery on staging | https://valdostadentalassociates.kinsta.cloud/ |  | Medium | Rebuild gallery with real case photos (with consent) | Crawl comparison | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Social Proof | Social media links | Fail |  |  |  | No social icons/links on staging (live site also has none). Practice has an active Facebook page per crosswalk | https://valdostadentalassociates.kinsta.cloud/ | facebook.com/valdostadentalassociates | Low | Add Facebook link to footer | HTML inspection + crosswalk | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Social Proof | Review schema | Fail |  |  |  | No aggregateRating/review schema | https://valdostadentalassociates.kinsta.cloud/ |  | Low | Add once reviews are on-site | HTML inspection | Medium
Mobile / UX — Weight 5% • Section score 50/100 (3 scored, 2 manual review)
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Mobile / UX | Viewport / zoom accessible | Pass |  |  |  | width=device-width, initial-scale=1; zoom not disabled | https://valdostadentalassociates.kinsta.cloud/ |  | Low | None | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Mobile / UX | Navigation clarity | Partial |  |  |  | Nav includes New Patients + Contact; mega-menu lists ~20 items across service categories | https://valdostadentalassociates.kinsta.cloud/ | Comprehensive but heavy; verify mobile menu usability | Medium | Test mobile menu collapse behavior | HTML inspection | Medium
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Mobile / UX | Image alt text | Fail |  |  |  | 0 of 10 homepage <img> tags have alt text (all alt="") | https://valdostadentalassociates.kinsta.cloud/ | Hurts accessibility AND image SEO on a brand-new build | High | Populate alt attributes on all content images | HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Mobile / UX | Branded 404 page | Needs Manual Review |  |  |  | 404s return HTTP 404; branding of the error page not visually verified | https://valdostadentalassociates.kinsta.cloud/this-page-does-not-exist-test-404 |  | Low | Check 404 template has nav + CTA | curl | Medium
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Mobile / UX | Readability / contrast | Needs Manual Review |  |  |  | Not assessable from static HTML; PSI a11y 85 suggests minor issues only | https://valdostadentalassociates.kinsta.cloud/ |  | Low | Spot-check in rendered browser | Manual review | Medium
Security / Compliance — Weight 5% • Section score 50/100 (4 scored, 1 manual review)
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Security / Compliance | HTTPS with valid SSL | Pass |  |  |  | Valid cert on kinsta.cloud; production domain cert will need verification at cutover | https://valdostadentalassociates.kinsta.cloud/ |  | Low | Verify SSL on production domain at launch | curl | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Security / Compliance | Privacy policy accessible | Fail |  |  |  | No privacy policy page or footer link found. Live site has /disclaimers/privacy_policy | https://valdostadentalassociates.kinsta.cloud/ | P0 for a healthcare practice website — HIPAA-adjacent requirement and a content REGRESSION vs live | High | Create /privacy-policy/ and link in footer before launch | Crawl + HTML inspection | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Security / Compliance | Disclaimer / terms | Fail |  |  |  | Live site's /disclaimers/disclaimer not carried over | https://valdostadentalassociates.kinsta.cloud/ |  | Medium | Recreate disclaimer page + footer link | Crawl comparison | High
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Security / Compliance | Accessibility statement | Needs Manual Review |  |  |  | 'Accessibility' text found in footer area but no confirmed link/page | https://valdostadentalassociates.kinsta.cloud/ |  | Medium | Confirm accessibility statement page exists and is linked | HTML inspection | Medium
Valdosta Dental Associates | https://valdostadentalassociates.kinsta.cloud/ | Security / Compliance | No mixed content | Pass |  |  |  | PSI Best Practices 100/100; no mixed-content flags | https://valdostadentalassociates.kinsta.cloud/ |  | Low | None | PageSpeed Insights | High

## Score Summary
Website Storefront Audit — STAGING BUILD REVIEW
Valdosta Dental Associates ¦ Staging: https://valdostadentalassociates.kinsta.cloud/ ¦ Live: https://www.thevaldostadentist.com/ ¦ Audited 2026-07-20
Weighted staging-build score. Manual-review items excluded from scoring.
Audit Section | Weight | Items | Scored | Manual Review | Section Score (/100) | Weighted Contribution
Technical Health | 15% | 14 | 13 | 1 | 61.5 | 9.22
Conversion & Contact | 25% | 12 | 10 | 2 | 70 | 17.5
Location Information | 10% | 7 | 5 | 2 | 90 | 9
Services | 15% | 7 | 6 | 1 | 66.7 | 10.01
Doctor / Team Trust | 10% | 6 | 5 | 1 | 60 | 6
Patient Resources | 10% | 7 | 7 |  | 35.7 | 3.57
Social Proof | 5% | 5 | 5 |  | 0 | 0
Mobile / UX | 5% | 5 | 3 | 2 | 50 | 2.5
Security / Compliance | 5% | 5 | 4 | 1 | 50 | 2.5
OVERALL STAGING BUILD SCORE | [5 empty] | 60.3 / 100
Scoring method
Pass = 1.0, Partial = 0.5, Fail = 0.0. 'Needs Manual Review' items are excluded from scoring. Section % × weight = contribution.
Launch Blockers (fix before go-live)
# | Section | Issue / Evidence | Recommended Fix
1 | Security / Compliance | Privacy policy + disclaimer pages missing (exist on live site — content regression) | Recreate both pages + footer links
2 | Technical Health | No 301 redirect map — all 18 legacy URLs 404 on the new build | Build + test full 301 map at cutover
3 | Technical Health | X-Robots-Tag noindex must be lifted on the production domain | Add to launch checklist; verify in GSC day 1
4 | Social Proof | Reviews page dropped (live has one; 4.3★/197 GBP reviews available) | Re-enable the commented-out reviews section
5 | Technical Health | Broken nav link /preventive-care/ (404) + Hello World post + generic homepage title | Fix link, delete cruft, rewrite title tag

## Live vs Staging
Website Storefront Audit — STAGING BUILD REVIEW
Valdosta Dental Associates ¦ Staging: https://valdostadentalassociates.kinsta.cloud/ ¦ Live: https://www.thevaldostadentist.com/ ¦ Audited 2026-07-20
Head-to-head comparison and full page-inventory map: every live-site URL and where it lands on the new build.
Head-to-Head Comparison
Metric | Live Site (thevaldostadentist.com) | Staging Build (kinsta.cloud) | Winner
Platform | Officite (legacy template, .html pages, 'Powered by Officite' footer) | WordPress 7.0.2 + Elementor 4.1.5 + WP Rocket, hosted on Kinsta | Staging
PSI mobile — Performance | 63 | 77 (LCP 3.8s vs live 8.1s) | Staging
PSI mobile — Accessibility | 86 | 85 | Tie
PSI mobile — Best Practices | 65 | 100 | Staging
PSI mobile — SEO | 92 | 61 (depressed by staging noindex header; re-test at launch) | Live*
Homepage title tag | 'Valdosta, GA Dentist - Valdosta Dental Associates - General Dentist' (67 chars, slightly long) | 'Home - Valdosta Dental Associates' (generic — no keyword/city) | Live
H1 discipline | 2 H1s (insurance banner + phone number) | 1 clean H1 ('Superior dentistry with a personal touch.') | Staging
Schema | MedicalBusiness + Dentist | Dentist (hours wrong: Mon–Sun 9–5) | Live
Pages in sitemap | 18 | 23 pages + 1 placeholder post | Staging
Individual service pages | ~4 (services hub + a few) | 13 dedicated service pages | Staging
Doctor bios | None (staff page has no bios) | 5 full bios w/ credentials + personal stories | Staging
Reviews page | Yes (/reviews) | MISSING (section built but commented out) | Live
Smile gallery | Yes (/smile-gallery) | MISSING | Live
Patient education library | Yes (Officite licensed library) | MISSING (likely can't migrate licensed content) | Live
Privacy policy / disclaimer | Yes (/disclaimers/*) | MISSING both | Live
Appointment path | /appointment-request page | Gravity Form on /contact/ + /new-patients/ | Tie
Online real-time scheduling | No | No (crosswalk: Scheduler Live = Not Live) | Tie
New patient offer | No | No | Tie
Click-to-call | Yes | Yes | Tie
Broken internal links | 0 found | 1 (/preventive-care/ nav 404) | Live
Oak St (VDO) location shown | No | No | Tie
Indexability | Indexable | noindex via X-Robots-Tag (staging default — must lift at launch) | —
Page Inventory Map — all 18 live-site URLs vs the new build
Live URL | Staging Equivalent | Status | Action Needed at Launch
/ | / | Carried over | None
/appointment-request | — (form now on /contact/ + /new-patients/) | Replaced | 301 → /contact/
/contact-us | /contact/ | Renamed | 301 → /contact/
/disclaimers/disclaimer | MISSING | Dropped — REGRESSION | Recreate page; 301 → new URL
/disclaimers/privacy_policy | MISSING | Dropped — REGRESSION (P0) | Recreate page; 301 → new URL
/emergency-appointments | /emergency-appointments/ | Carried over | 301 (trailing slash)
/extractions | /extractions/ | Carried over | 301 (trailing slash)
/extractions-with-iv-sedation | /iv-sedation/ | Renamed | 301 → /iv-sedation/
/general-dentistry | /general-dentistry/ | Carried over | 301 (trailing slash)
/my-blog | /blog/ | Renamed (both empty) | 301 → /blog/
/new-patients | /new-patients/ | Carried over | 301 (trailing slash)
/office | — (closest: /staff/ + /contact/) | Dropped | 301 → /staff/ or build About page
/patient-education | MISSING | Dropped (licensed Officite library) | Confirm intentional; 301 → /blog/ or /
/preventative-tips-for-children | /preventative-tips-for-children/ | Carried over | 301 (trailing slash)
/reviews | MISSING (built but commented out) | Dropped — REGRESSION | Re-enable reviews; 301 → /reviews/
/services | — (replaced by 13 individual pages) | Replaced (improvement) | 301 → /general-dentistry/ or services hub
/smile-gallery | MISSING | Dropped — REGRESSION | Rebuild gallery; 301 → /cosmetic-dentistry/
/staff | /staff/ | Carried over (upgraded w/ bios) | 301 (trailing slash)
NEW pages on staging that don't exist on live (13 service pages — net SEO gain)
/dental-crowns/ | New service page | Addition
/cosmetic-dentistry/ | New service page | Addition
/family-care/ | New service page | Addition
/preventative-care/ | New service page | Addition
/scaling-and-root-planning/ | New service page | Addition
/root-canal-therapy/ | New service page | Addition
/sealants/ | New service page | Addition
/teeth-whitening/ | New service page | Addition
/veneers/ | New service page | Addition
/fillings/ | New service page | Addition
/specialty-dentures/ | New service page | Addition
/dental-bridges/ | New service page | Addition
/dental-bonding/ | New service page | Addition